## Sheet1
Sl No. | User Stories | Priority | Estimated Time
1 | User can browse local files | 2 | 4 days
2 | User can create new file | 2 | 2 days
3 | User can create new folder | 2 | 1 day
4 | User can delete files and folders | 2 | 7 days
5 | User can rename files and folders | 2 | 5 days
6 | User can open files, folders and shortcut files | 2 | 4 days
7 | User can add, edit, delete, test ssh connections | 1 | 13 days
8 | User can browse SSH files | 1 | 2 days
9 | User can create new file/folder | 1 | 1 day
10 | User can delete/rename files/folders | 1 | 5 days
11 | User can open folders | 1 | 3 days
12 | User can copy/paste files/folders | 1 | 7 days
13 | User can cut/paste files/folders | 1 | 1 day